## Instructions
ITC327W Phase 2 Project Progress Tracker
Use this workbook during Phase 2: System Architecture and Design. Update it throughout the phase and submit the same workbook with Assessment 2.
Sheet | Purpose | What must be kept current
Project Overview | Group details and automatic progress summary | Group information, GitHub link and current Phase 2 progress
Design Progress | Track each design artefact and supporting work | Architecture, UML, ERD, mobile/web interfaces, SRS and project-management tasks
Individual Contributions | Record work personally completed by each student | Activity, responsibility, work completed and evidence
Design Source Links | Record editable source links/files for submitted designs | Architecture, UML, ERD, mobile and web design sources
Challenges & Actions | Record design/project challenges and corrective action | Problem, effect, action, owner, target date and status
Phase Summary | Summarise what was achieved and what remains | Phase status, completed work, gaps and next priorities
Group Reflection | One shared group reflection for Phase 2 | Participation, collaboration, challenges, learning and improvements
Important
Do not create a separate tracker for each activity. This Phase 2 workbook is updated as the group progresses. Evidence may include GitHub commits, screenshots, document sections, editable design links/files and other appropriate project evidence. Do not include passwords, API keys or confidential stakeholder information.

## Project Overview
Phase 2 Project Overview
Group | Group V | Phase 2 Progress Summary
Project Title | Digital Maintenance Complaint System | Total tracked items | 12
Stakeholder / Organisation | CUT Estate and Infrastructure | Completed | 12
Group Leader | Asande Mkabela | In Progress | 0
Number of Group Members | 6 | Blocked | 0
GitHub Repository Link |  | Average completion | 100%
Reporting Period
Overall Phase Status | Not Started | Phase 2 Reminder
Phase 2 focuses on system architecture and design. Track the design artefacts, the editable source links/files, individual contributions, challenges, Microsoft Project updates and GitHub evidence. No separate stakeholder-evidence section is required in this tracker.

## Design Progress
Phase 2 Design Progress
Task ID | Design / Project Item | Description / Expected Output | Responsible Student(s) | Planned Date | Actual Completion Date | Status | % Complete | Evidence / Link | Notes / Action Required
P2-01 | System Architecture | Overall architecture showing Flutter, ASP.NET and shared Supabase backend | Tsebano Stemer | 2026-09-18 | 2026-10-06 | Completed | 100% | System Architecture Diagram | The system architecture diagram was too detailed and fell out of the boundaries of what was expected from the group,the group had to go back and design a system architecture that was required.
P2-02 | Use Case Diagram | Actors, use cases, system boundary and appropriate UML relationships | Thabang Motaung | 2026-09-20 | 2026-09-20 | Completed | 100% | Use Case Diagram | The Use Case diagram was completed on time and was used to design the next design which is the Sequence diagram
P2-03 | Sequence Diagram 1 | Important Flutter process | Vuyisile Fihlo | 2026-09-23 | 2026-09-24 | Completed | 100% | Sequence Diagram | The Sequence Diagram took a day longer as there was brainstorming amongst the Group Members of how the sequence of the processes would go on the Mobile Application
P2-04 | Sequence Diagram 2 | Important ASP.NET process | Vuyisile Fihlo | 2026-09-23 | 2026-09-24 | Completed | 100% | Sequence Diagram | The Sequence Diagram took a day longer as there was brainstorming amongst the Group Members of how the sequence of the processes would go on the Web Application
P2-05 | ERD | Entities, attributes, PKs, FKs, relationships and cardinality | Sisekelo Mtshali | 2026-09-23 | 2026-10-06 | Completed | 100% | Entity Relationship Diagram | The ERD diagram took longer than expected as it turned out to be the design with the most workload as compared to the rest.There was a little bit of confusion which was straightened out during the group's second consultation
P2-06 | Flutter Interface Designs | Main mobile screens and navigation | Katleho Mphomela | 2026-10-09 | 2026-10-09 | Completed | 100% | Mobile Application Prototypes | Flutter interface designs were completed on the planned date using the figma platform. The Use case as well as the sequence diagram were the inputs used to complete the Flutter interface design
P2-07 | ASP.NET Interface Designs | Main web pages and navigation | Asande Mkabela | 2026-10-09 | 2026-10-09 | Completed | 100% | Web Application Prototypes | The ASP.Net interface designs were completed on the planned date using the figma platform. The Use case as well as the sequence diagram were the inputs used to complete the ASP.Net interface design
P2-08 | Design Alignment | Requirements linked across UML, ERD and interfaces | All Members | 2026-10-10 | 2026-10-10 | Completed | 100% | Links | frfrfrf
P2-09 | Updated SRS | Phase 2 architecture and design section inserted in existing SRS | Sisekelo Mtshali | 2026-10-10 | 2026-10-10 | Completed | 100% | Updated SRS Document | The Updated SRS document was completed on the Planned date and consists of all the architecture and designs that were done during phase 2
P2-10 | Microsoft Project | Schedule updated to reflect design progress and upcoming development | Asande Mkabela | 2026-10-10 | 2026-10-11 | Completed | 100% | Updated Microsoft Project Schedule | The Microsoft Project schedule was successfully updated with the accurate dates and also with future plans going forward
P2-11 | GitHub | Current design documentation and repository organisation | All Members | 2026-10-11 | 2026-10-11 | Completed | 100% | GitHub Repository Linl | All the Phase 2 documentations and links were pushed into GitHub by all members.The only task left now is to prepare for the phase 2 presentation which is on the 16th of October
P2-12 | Phase 2 Presentation | Presentation and defence preparation | All Members | 2026-10-15 | 2026-10-15 | Completed | 100% | Phase 2 Presentation | The phase 2 presentaion are currently going well and evryone is getting prepared to present their designated part

## Individual Contributions
Phase 2 Individual Contributions
Student Name | Student Number | Activity / Artefact | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Quality / Review Notes | Contribution Status
Tsebano Stemer |  | Overall architecture showing Flutter, ASP.NET and shared Supabase backend | System Architecture Diagram Designer | Designed the overall System Architecture Diagram showing Flutter, ASP.NET and shared Supabase backend |  |  |  | Yes | 2026-10-06 | The system architecture diagram was too detailed and fell out of the boundaries of what was expected from the group,the group went back and made sure that a correc,accurate architecture diagram was designed and fit for submission | Completed
Thabang Motaung | 224120586 | Actors, use cases, system boundary and appropriate UML relationships | Use case Diagram Designer | Designed the Use Case Diagram with the Actors and their use cases along with the appropiate UML relationships |  |  |  | Yes | 2026-09-20 | The Use Case was not complete during the group's first consultation session but eventually it was completed, fully detailed and verified good for submission | Completed
Vuyisile Fihlo | 224049675 | Important Flutter process,Important ASP.NET process | Sequence Diagram Designer | Designed a Sequence Diagram showing Important Flutter and ASP.NET processes and sequencing |  |  |  | Yes | 2026-09-24 | The Sequence diagram shows every important process and logical sequence of both the mobile application and the web application | Completed
Katleho Mphomela | 224005352 | Main mobile screens and navigation | Mobile Application Prototype Designer | Created a flutter mobile application prototype showing the main mobile screens and sequential navigation |  |  |  | Yes | 2026-10-09 | The Flutter mobile application was accurately detailed giving a proper picture of how the final application would look | Completed
Asande Mkabela | 224063746 | Main web pages and navigation | Web Application Prototype Designer | Created an ASP.NET web application prototype showing the main web screens and sequential navigation |  |  |  | Yes | 2026-10-09 | The ASP.NET web application was accurately detailed giving a proper picture of how the final application would look | Completed
Sisekelo Mtshali | 224124382 | Entities, attributes, PKs, FKs, relationships and cardinality. Phase 2 architecture and design section inserted in existing SRS | Entity Relationship Diagram Designer | Designed an Entity Relationship Diagram to visually model the data structure and relationships within a database system before writing code |  |  |  | Yes | 2026-10-06 | The ERD was accurately designed with clear and easy to understand relationships | Completed
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started

## Design Source Links
Phase 2 Original Design Source Links / Files
Design Artefact | Tool Used | Editable Link / File Name | Accessible to Lecturer? | Last Updated | Responsible Student | Included in SRS? | Notes
System Architecture | Lucid Chart |  | Yes | 2026-10-06 | Tsebano Stemer | No
Use Case Diagram | Lucid Chart |  | Yes | 2026-09-20 | Thabang Motaung | No
Sequence Diagram 1 | Lucid Chart |  | Yes | 2026-09-24 | Vuyisile Fihlo | No
Sequence Diagram 2 | Lucid Chart |  | Yes | 2026-09-24 | Vuyisile Fihlo | No
ERD | Lucid Chart |  | Yes | 2026-10-06 | Sisekelo Mtshali | No
Flutter Interface Designs | Figma |  | Yes | 2026-10-09 | Katleho Mphomela | No
ASP.NET Interface Designs | Figma |  | Yes | 2026-10-09 | Mkabela Asande | No
Navigation Flow | Figma |  | Yes | 2026-10-09 | Katleho Mphomela & Asande Mkabela | No

## Challenges & Actions
Phase 2 Challenges and Corrective Actions
Date Identified | Challenge | Effect on Progress / Design | Corrective Action | Responsible Student | Target Date | Status | Resolved Date | Notes
2026-10-01 | The initial System architecture was too much detailed and fell out of the boundaries of what was required from the group in terms of the System Architecture Design | The Effect of this challenge was not that severe as the group was able to understand the initial design so we went along to design the use case diagram while fixing the System Architecture Design to ensure that it falls within the standard of what was required | The responsible student went to fix the System Architecture Design using the provided notes on the School''s blackboard | Tsebano Stemer | 2026-10-06 | Completed | 2026-10-06 | The System architecture was properly fixed to meet the standard of the requirements by the lecturers. The lesson that the group learnt was to use information provided by the lecturers and not rely on external information from platforms like YouTube
2026-10-03 | Difficulty of the Group having a physical meeting | The effect of this challenge was delayed progress as some of the group members were not able to finish their tasks on time due to lack of resources. | The group would organise teams meetings and work on their designated taks. If a member wasn't able to complete their tasks, the tasks would be reassigned to another group member until the initial assigned member is back to being able to carry on with their tasks | All Members | 2026-10-10 | Completed | 2026-10-12 | The Corrective Action came to rescue as the group was able to finish their phase 2 tasks before the submission date. The lesson learnt is that challenges will always be there and the most important thing is how they are handled so they don't delay progess dismally
2026-10-01 | High Complexity in the Database Entity Modelling | The effect of this challenge was very severe as it delayed progress | The Group decided to team on this aspect of the project and design a logical and easy to understand ERD while not compromising the important elements of our system | Sisekelo Mtshali, All Members | 2026-10-06 | Completed | 2026-10-06 | The challenge was resolved within time and the group was able to come up with logical ERD.
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Phase Summary
Phase 2 Progress Summary
Reporting Period | 19 Sept 2026 – 12 Oct 2026, | Phase 2 Completion Checklist | Complete?
Overall Phase Status | In Progress | Architecture complete | Yes
What was completed during Phase 2? | The System Architecture, Use Case Diagram, Two Sequence Diagrams, The ERD, Flutter Interfaces, ASP.NET Interfaces, Editable source links, the SRS is Updated, Updated Microsoft Project, GitHub | Use Case Diagram complete | Yes
What remains incomplete? | None | Two Sequence Diagrams complete | Yes
Why is it incomplete? | N/A | ERD complete | Yes
Which contributions were particularly important? | Architecture Design, Use Case Diagram, the two Sequence Diagrams,ERD, Flutter Interfaces, ASP.NET interfaces, Updated SRS, Updated Microsoft Project | Flutter interfaces complete | Yes
Were there participation concerns? | None | ASP.NET interfaces complete | Yes
What will the group improve in Phase 3? |  | Editable source links/files recorded | No
Main priority for Phase 3 | The Priority of phase 3 is set to setting up Supabase, building Flutter app UI, and developing ASP.NET web admin dashboard. | SRS updated | Yes
|  | Microsoft Project updated | Yes
|  | GitHub current | No
|  | Individual contributions recorded | Yes
|  | Challenges/actions updated | Yes
|  | Group reflection completed | No

## Group Reflection
Phase 2 Group Reflection
1. What did the group complete successfully during Phase 2?
2. Which architecture or design activities were the most challenging?
3. How did the group ensure that Flutter, ASP.NET and Supabase were designed as one integrated system?
4. How was work divided among group members, and was participation balanced?
5. What did the group learn from developing the UML, ERD and interface designs?
6. What will the group do differently during development in Phase 3?