## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group V | Completed | 11
Project title | Digital Maintenance Complaint Lifecycle Management System | In Progress | 0
Stakeholder or organisation | CUT Estate and Infrastructure Department | Not Started | 0
Group mentor | Ms Mbele | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | 2026/08/20 - 2026/09/04 | Overdue | 0
Overall status | Completed
Overall % complete | 91.67% | Contribution Summary | Count
Main achievement | Found and Identified a stakeholder to work with | Contribution entries | 8
Main challenge | Unclear requirements from the stakeholder | Verified entries | 8
Next planned activity | Conduct a feasibility study, prepare a project risk register and refine the SRS and project plan | Unverified entries | 0
|  | Stakeholder engagements | 1

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Sisekelo Mtshali | 2026-08-17 | 2026-08-19 | Completed | 100 | Stakeholder Profile | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Motaung Thabang | 2026-08-20 | 2026-08-22 | Completed | 100 | The SRS Document | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Sisekelo Mtshali | 2026-08-22 | 2026-08-24 | Completed | 100 | The SRS Document | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Fihlo Vuyisile | 2026-08-24 | 2026-08-25 | Completed | 100 | Stakeholder Interview Questions | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Malefetsane Tabi | 2026-08-25 | 2026-08-26 | Completed | 100 | Meeting Notes | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Tlotliso Kasa | 2026-08-28 | 2026-08-30 | Completed | 100 | The Complete SRS Document | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Mkabela Asande | 2026-08-28 | 2026-08-29 | Completed | 100 | Microsoft project File | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Mphomela Katleho | 2026-08-28 | 2026-08-28 | Completed | 100 | GitHub Repo Link | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Stemer Tsebano | 2026-08-29 | 2026-08-30 | Completed | 100 | Supabase Project Screenshots | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Motaung Thabang | 2026-08-31 | 2026-09-02 | Completed | 100 | Updated Excel Project Progress tracker workbook | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | All Members | 2026-09-03 | 2026-09-04 | Completed | 100 | Excel Progress report | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Malefetsane Tabi | 224005352 | Unit 1 / Phase 1 | Activity 1.1, 1.2,1.3 | Conduct and document the stakeholder interview | Conducted and documented the stakeholder interview | 2026-08-26 | 7 | Meeting Notes | Yes | 2026-09-04 | Interview conducted successfully and the document was well compiled
Motaung Thabang | 224120586 | Unit 1 / Phase 1 | Activity 1.1, 1.2,1.3 | Document the current process and problem | Documented the current process and problem | 2026-08-22 | 10 | The Software Requirement Specification Document | Yes | 2026-09-04 | The document of the current process and problem was well defined
Mphomela Katleho | 224124912 | Unit 1 / Phase 1 | Activity 1.1, 1.2,1.3 | Create and configure the GitHub repository | Created and configured the GitHub repository | 2026-08-28 | 8.5 | GitHub Link | Yes | 2026-09-04 | The GitHub Repository works exceptionally well
Sisekelo Mtshali | 224124382 | Unit 1 / Phase 1 | Activity 1.1, 1.2,1.3 | Identify and confirm the external stakeholder | Identified and confirmed the external stakeholder | 2026-08-19 | 10 | Stakeholder Profile | Yes | 2026-09-04 | The Stakeholder was found and gave confirmation
Mkabela Asande | 224063746 | Unit 1 / Phase 1 | Activity 1.1, 1.2,1.3 | Create the initial Microsoft Project schedule | Created the initial Microsoft Project schedule | 2026-08-29 | 12.5 | Microsoft Project File | Yes | 2026-09-04 | A good Microsoft project schedule that has perfect scheduling
Kasa Tlotliso | 224086876 | Unit 1 / Phase 1 | Activity 1.1, 1.2,1.3 | Compile the initial SRS | Compiled the initial SRS | 2026-08-30 | 11 | The Completed Software Requirement Specification Document | Yes | 2026-09-04 | SRS is well compiled and has all the necessary information
Stemer Tsebano | 222022131 | Unit 1 / Phase 1 | Activity 1.1, 1.2,1.3 | Create the initial Supabase project | Created the initial Supabase project | 2026-08-30 | 5.5 | Supabase Link | Yes | 2026-09-04 | Supabase project is created
Fihlo Vuyisile | 224049675 | Unit 1 / Phase 1 | Activity 1.1, 1.2,1.3 | Prepare stakeholder interview questions | Prepared stakeholder interview questions | 2026-08-25 | 5 | Interview Questions | Yes | 2026-09-04 | Interview questions managed to get us all the necessary information

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-25 | Unit 1 / Phase 1 | Meeting | Conduct Stakeholder Interview to gain more insights about the Stakeholder's current process, to conduct a clear problem statement and gather all necessary information | Fihlo Vuyisile, Sisekelo Mtshali, Mphomela Katleho, Motaung Thabang, Mkabela Asande, Tlotliso Kasa, Stemer Tsebano & Malefetsane Tabi | Mr Khumalo | The central problem experienced by CUT is inefficient and fragmented maintenance complaint management resulting from the absence of a centralized digital system for reporting, assigning, monitoring, escalating, resolving and evaluating maintenance complaints. | Create a project intended to improve the way maintenance complaints are reported, processed, monitored, resolved and verified | Meeting Notes

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-25 | Unit 1 / Phase 1 | Unclear Requirements from the Stakeholder | Delayed agreement on the way forward and how the system should look or behave | One of our group member is a member of the House Committee so he was able to explain the current process of the system currently in use. | Sisekelo Mtshali | 2026-08-25 | Resolved
2026-08-25 | Unit 1 / Phase 1 | Unavailability of the Stakeholder | No photographic evidence of our meetings with the Stakeholder | We resorted to using meeting notes as evidence of engangement with the Stakeholder | All Students | 2026-09-04 | Open
2026-08-19 | Unit 1 / Phase 1 | Not enough time to complete all our stages of Phase 1 | Pressurised approach of completing the phase 1 stage of the project due to trying to meet the deadline | Due date was extended from the 31st of August to the 4th of Septemeber | None | 2026-09-04 | Resolved
2026-08-28 | Unit 1 / Phase 1 | Unable to have a physical meeting due to bad weather conditions on that particular day | A day lost | All the group members had a teams meeting to discuss what was meant to be discussed | All Students | 2026-08-29 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 2026/08/17 - 2026/09/04 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Stakeholder Identification,described the current process, writing of the problem statement, Definition of the initial project scope, Assigned interview roles, prepared the interview questions,interview conduction, Organize the findings, Compiled the SRS, Created the Microsoft Project Schedule, Created the GitHub Repository, Created the SupaBase Project and Completed the Project Progress Workbook | Stakeholder engagement recorded | Yes
What remains incomplete? | None | Challenges and actions updated | Yes
Why is it incomplete? | n/a | Group reflection completed | Yes
Which contributions were particularly important? | Identifying the external stakeholder,documenting the current process and problem,defining the project aim, objectives and scope, preparing stakeholder interview questions, compiling the initial SRS,creating the initial MS Project schedule and Completing the progress report | Microsoft Project updated | Yes
Were there participation concerns? | No there were no participation concerns, every group member participated to their best capabilities. | GitHub evidence available | Yes
What will the group improve in the next phase? | In the next phase the group will improve one of the biggest obstacle we had in phase one which is Time Management | Confidential peer check completed | Yes
Main priority for the next phase | Conduct a feasibility study, prepare a project risk register and refine the SRS and project plan

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Estate and Infrastructure Department and the maintenance of CUT residences | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | One of the most important lessons we learned was that understanding the stakeholder's actual problem before designing the system is essential. Through our stakeholder engagement, we gained a clearer understanding that the main problem at CUT was the inefficient and fragmented management of maintenance complaints and the need for a centralised digital system to report, assign, monitor, escalate, resolve and evaluate maintenance issues. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Several aspects of the project went well. The group successfully identified and confirmed the external stakeholder, documented the current process and problem, prepared stakeholder interview questions, conducted the stakeholder interview, organised the findings and compiled the initial Software Requirements Specification.. These achievements were possible because tasks were divided among group members according to specific responsibilities, allowing each member to contribute to the completion of Phase 1. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | The group experienced several challenges. Initially, some stakeholder requirements were unclear, which delayed agreement on how the system should behave. We addressed this challenge by using information from a group member who is familiar with the House Committee and the current maintenance complaint process. Another challenge was the limited availability of the stakeholder, which made it difficult to obtain photographic evidence of stakeholder meetings. Time management was another major challenge because the group had limited time to complete all Phase 1 activities, which created pressure near the deadline. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided according to each group member's strength,capabilities and also interests
Did all members contribute fairly? Explain. | All group members contributed fairly and completed their assigned responsibilities. Tasks were divided fairly and equally, the tasks also came with the due date and no one submitted late or an uncomplete task. Before proceeding on something everyone came up with an idea or suggestion on how we can undertake a certain situation as well as the advantage of taking their approach, however an idea or suggestion with the most votes were taken.
How did the group handle disagreements or delays? | When disagreements occurred within the group, we openly communicated and discussed them. Each and every group member is given the opportunity to express their opinion and suggest what's the best way to move forward. If an agreement couldn't be reached we opted for voting and the suggestion with the major votes won. When delays occured we reshared tasks and made sure that we found the root of the delay.
What did the group learn from the stakeholder? | From engaging with the stakeholder, we learned that understanding the actual problem faced by an organisation is very necessary before developing a system. At first, we thought that our system mainly needed to allow students to report maintenance problems. However, after learning more about the current process, we realised that reporting the problem is one of the many aspects.
Improvement action 1 for the next phase | Improve communication and coordination with the stakeholder.
Improvement action 2 for the next phase | Improve task planning and progress monitoring.
Priority for the next phase | The priority for the next phase is to conduct a feasibility study, prepare a project risk register and refine the SRS and project plan